## Daily View
Teaching Studio MVP - provisional 28 working days
Select Day 1 to Day 28 to view the shared functionality and four individual assignments.
Select day | Day 1 |  |  |  | Overall completion
Shared functionality
Whole-team outcome
Day accepted when
Team member | Role | Individual task | Expected output | Status | Project status | Value | Meaning | Action
[5 empty] | Tasks completed |  | Individual assignments completed | Update each person’s row separately
[5 empty] | Days completed |  | Full four-person workdays completed | Close all four rows during the daily review
[5 empty] | Days remaining |  | Workdays still open | Finish current work before pulling future tasks
[5 empty] | Final planned day |  | Last day in the 28-day sequence | Holidays do not consume a project day
[5 empty] | Current state |  | Overall project state | Record blockers in the Schedule sheet
How the team uses this tracker
1 | Start of day | Read the shared feature, then each member starts only their own assigned row.
2 | During the day | Rahul, Poojitha and Dhanunjaya complete their rotating roles independently; Teja prepares and runs QA.
3 | Before closing | Each person updates status and evidence for their own row. Discuss blockers together.
4 | End-of-day review | Review all four outputs together and close the day only when the shared completion rule is met.

## Schedule
28-working-day Teaching Studio MVP implementation plan ? corrected
Provisional effort sequence, not a committed delivery date. Reuse React/Vite, Express, PostgreSQL/Supabase and existing LMS identity. Advance only after acceptance evidence; see Scope and Gates.
Day | Shared application functionality | Whole-team outcome | Team member | Role | Individual task | Expected output | Individual done when | Day accepted when | Status | Progress | Blocker / dependency | Evidence / update
Day 1 | Project requirements and LMS integration scope | Agree what Teaching Studio reuses from the LMS and what must be added. | Rahul | Backend | Backend — Review LMS authentication, curriculum, content and teaching-session services; record reusable services. | Reviewed LMS reuse/gap inventory and BR-01?BR-36 traceability entries for Backend | Repository paths, existing capability, gap, owner and acceptance evidence are recorded; code delivery is not required for this analysis task. | The team has one agreed reuse-and-gap baseline for the existing LMS. | Needs verification | 0% | None | Prior tracker claimed complete. Unverified in reviewed checkout. Claimed evidence: Team confirmed Day 1 complete. Attach commit, commands/results and reviewer before closing.
Day 1 | Project requirements and LMS integration scope | Agree what Teaching Studio reuses from the LMS and what must be added. | Poojitha | Frontend | Frontend — Review required Studio screens, layouts and resource flows; record UI gaps. | Reviewed LMS reuse/gap inventory and BR-01?BR-36 traceability entries for Frontend | Repository paths, existing capability, gap, owner and acceptance evidence are recorded; code delivery is not required for this analysis task. | The team has one agreed reuse-and-gap baseline for the existing LMS. | Needs verification | 0% | None | Prior tracker claimed complete. Unverified in reviewed checkout. Claimed evidence: Team confirmed Day 1 complete. Attach commit, commands/results and reviewer before closing.
Day 1 | Project requirements and LMS integration scope | Agree what Teaching Studio reuses from the LMS and what must be added. | Dhanunjaya | Database | Database — Review the current LMS schema against Teaching Studio entities; record mapping gaps. | Reviewed LMS reuse/gap inventory and BR-01?BR-36 traceability entries for Database | Repository paths, existing capability, gap, owner and acceptance evidence are recorded; code delivery is not required for this analysis task. | The team has one agreed reuse-and-gap baseline for the existing LMS. | Needs verification | 0% | None | Prior tracker claimed complete. Unverified in reviewed checkout. Claimed evidence: Team confirmed Day 1 complete. Attach commit, commands/results and reviewer before closing.
Day 1 | Project requirements and LMS integration scope | Agree what Teaching Studio reuses from the LMS and what must be added. | Teja | QA | QA — Create the first acceptance checklist from the BRD and guides. | Reviewed LMS reuse/gap inventory and BR-01?BR-36 traceability entries for QA | Repository paths, existing capability, gap, owner and acceptance evidence are recorded; code delivery is not required for this analysis task. | The team has one agreed reuse-and-gap baseline for the existing LMS. | Needs verification | 0% | None | Prior tracker claimed complete. Unverified in reviewed checkout. Claimed evidence: Team confirmed Day 1 complete. Attach commit, commands/results and reviewer before closing.
Day 2 | Resource Library model and safe local setup | Prepare the Resource Library architecture without changing hosted production data. | Rahul | Database | Database — Draft resource items, versions, bindings and supporting tables; document the LMS identity mismatch. | Reviewed resource schema/service/UI/test design for Database | Design is mapped to current LMS integer identities and client/school scope; local-only execution and migration assumptions are documented. | The schema draft, integration risks and local test approach are documented. | Needs verification | 0% | Day 1 | Prior tracker claimed complete. Unverified in reviewed checkout. Claimed evidence: review/day2_schema_review.md. Attach commit, commands/results and reviewer before closing.
Day 2 | Resource Library model and safe local setup | Prepare the Resource Library architecture without changing hosted production data. | Poojitha | Backend | Backend — Define resource, version and binding service boundaries and access rules. | Reviewed resource schema/service/UI/test design for Backend | Design is mapped to current LMS integer identities and client/school scope; local-only execution and migration assumptions are documented. | The schema draft, integration risks and local test approach are documented. | Needs verification | 0% | Day 1 | Prior tracker claimed complete. Unverified in reviewed checkout. Claimed evidence: review/day2_schema_review.md. Attach commit, commands/results and reviewer before closing.
Day 2 | Resource Library model and safe local setup | Prepare the Resource Library architecture without changing hosted production data. | Dhanunjaya | Frontend | Frontend — Define the catalog, search, version and placement information required by the UI. | Reviewed resource schema/service/UI/test design for Frontend | Design is mapped to current LMS integer identities and client/school scope; local-only execution and migration assumptions are documented. | The schema draft, integration risks and local test approach are documented. | Needs verification | 0% | Day 1 | Prior tracker claimed complete. Unverified in reviewed checkout. Claimed evidence: review/day2_schema_review.md. Attach commit, commands/results and reviewer before closing.
Day 2 | Resource Library model and safe local setup | Prepare the Resource Library architecture without changing hosted production data. | Teja | QA | QA — Prepare schema, version immutability and tenant-isolation test cases. | Reviewed resource schema/service/UI/test design for QA | Design is mapped to current LMS integer identities and client/school scope; local-only execution and migration assumptions are documented. | The schema draft, integration risks and local test approach are documented. | Needs verification | 0% | Day 1 | Prior tracker claimed complete. Unverified in reviewed checkout. Claimed evidence: review/day2_schema_review.md. Attach commit, commands/results and reviewer before closing.
Day 3 | Integrated Teaching Studio authoring foundation in the LMS | Establish the complete shared foundation: protected LMS access, the authoring workspace and layouts, safe local data setup, and QA coverage. | Rahul | Backend | Backend — Connect the protected Studio route to existing LMS role access. | Working API/service for Integrated Teaching Studio authoring foundation in the LMS | The service/API works with permissions and error handling and is ready for QA. | Role-based access works, the authoring workspace and layouts render, the local data foundation is usable, and QA has verified the combined flow. | Needs verification | 0% | Days 1?2; confirm provisional LMS mapping before local implementation | Prior tracker claimed complete. Unverified in reviewed checkout. Claimed evidence: docs/teaching-studio-day3.md. Attach commit, commands/results and reviewer before closing. Studio routes/canvas and cited day3 document were not found in reviewed application source; SQL files alone do not verify this gate.
Day 3 | Integrated Teaching Studio authoring foundation in the LMS | Establish the complete shared foundation: protected LMS access, the authoring workspace and layouts, safe local data setup, and QA coverage. | Poojitha | Database | Database — Prepare the local migration/seed foundation needed for safe Studio testing. | Reviewed schema, migration or data change for Integrated Teaching Studio authoring foundation in the LMS | The schema/query change runs locally, preserves integrity and is ready for QA. | Role-based access works, the authoring workspace and layouts render, the local data foundation is usable, and QA has verified the combined flow. | Needs verification | 0% | Days 1?2; confirm provisional LMS mapping before local implementation | Prior tracker claimed complete. Unverified in reviewed checkout. Claimed evidence: docs/teaching-studio-day3.md. Attach commit, commands/results and reviewer before closing. Studio routes/canvas and cited day3 document were not found in reviewed application source; SQL files alone do not verify this gate.
Day 3 | Integrated Teaching Studio authoring foundation in the LMS | Establish the complete shared foundation: protected LMS access, the authoring workspace and layouts, safe local data setup, and QA coverage. | Dhanunjaya | Frontend | Frontend — Implement the 1920 × 1080 canvas, safe margins and 14 target layouts. | Working UI/component for Integrated Teaching Studio authoring foundation in the LMS | The UI works in the agreed flow and is ready for QA. | Role-based access works, the authoring workspace and layouts render, the local data foundation is usable, and QA has verified the combined flow. | Needs verification | 0% | Days 1?2; confirm provisional LMS mapping before local implementation | Prior tracker claimed complete. Unverified in reviewed checkout. Claimed evidence: docs/teaching-studio-day3.md. Attach commit, commands/results and reviewer before closing. Studio routes/canvas and cited day3 document were not found in reviewed application source; SQL files alone do not verify this gate.
Day 3 | Integrated Teaching Studio authoring foundation in the LMS | Establish the complete shared foundation: protected LMS access, the authoring workspace and layouts, safe local data setup, and QA coverage. | Teja | QA | QA — Run layout, viewport, route-access, build and browser checks. | Executed test results and defect update for Integrated Teaching Studio authoring foundation in the LMS | Planned tests are executed, and pass/fail evidence and defects are recorded. | Role-based access works, the authoring workspace and layouts render, the local data foundation is usable, and QA has verified the combined flow. | Needs verification | 0% | Days 1?2; confirm provisional LMS mapping before local implementation | Prior tracker claimed complete. Unverified in reviewed checkout. Claimed evidence: docs/teaching-studio-day3.md. Attach commit, commands/results and reviewer before closing. Studio routes/canvas and cited day3 document were not found in reviewed application source; SQL files alone do not verify this gate.
Day 4 | Confirm existing LMS tenant and curriculum mapping | Review and accept the mapping already present in Studio SQL, then resolve remaining identity, school and academic-scope gaps. | Rahul | Frontend | Frontend ? Map existing programme/grade/subject/chapter/topic selectors and role navigation to the approved Studio contract. | Working UI/component for Tenant and curriculum integration decision | The UI works in the agreed flow and is ready for QA. | One reviewed adapter contract maps client_id, optional school_id, integer LMS users and academic IDs; Author authority and platform-owned content behavior are explicit. | Planned | 0% | Days 1?3 evidence; review existing SQL 001?004
Day 4 | Confirm existing LMS tenant and curriculum mapping | Review and accept the mapping already present in Studio SQL, then resolve remaining identity, school and academic-scope gaps. | Poojitha | Backend | Backend ? Reuse existing JWT authentication, permission and entitlement services; map content_authorizer to scoped Author capabilities without granting blanket academic approval. | Working API/service for Tenant and curriculum integration decision | The service/API works with permissions and error handling and is ready for QA. | One reviewed adapter contract maps client_id, optional school_id, integer LMS users and academic IDs; Author authority and platform-owned content behavior are explicit. | Planned | 0% | Days 1?3 evidence; review existing SQL 001?004
Day 4 | Confirm existing LMS tenant and curriculum mapping | Review and accept the mapping already present in Studio SQL, then resolve remaining identity, school and academic-scope gaps. | Dhanunjaya | Database | Database ? Review existing Studio client/user/program/curriculum foreign keys and tenant constraints; document any required migration changes. | Reviewed schema, migration or data change for Tenant and curriculum integration decision | The schema/query change runs locally, preserves integrity and is ready for QA. | One reviewed adapter contract maps client_id, optional school_id, integer LMS users and academic IDs; Author authority and platform-owned content behavior are explicit. | Planned | 0% | Days 1?3 evidence; review existing SQL 001?004
Day 4 | Confirm existing LMS tenant and curriculum mapping | Review and accept the mapping already present in Studio SQL, then resolve remaining identity, school and academic-scope gaps. | Teja | QA | QA — Check the proposed mapping against cross-tenant, role and academic-scope scenarios. | Executed test results and defect update for Tenant and curriculum integration decision | Planned tests are executed, and pass/fail evidence and defects are recorded. | One reviewed adapter contract maps client_id, optional school_id, integer LMS users and academic IDs; Author authority and platform-owned content behavior are explicit. | Planned | 0% | Days 1?3 evidence; review existing SQL 001?004
Day 5 | Lesson, session and screen contract | Define exactly what the Author creates and what the LMS stores. | Rahul | Database | Database — Define lesson, session, screen, objective and ordering relationships. | Reviewed lesson/session/screen/object contract for Database | UI fields, service commands, existing/new tables, validation, revision handling and permission boundaries agree; implementation follows on Days 6?8. | One reviewed contract covers UI fields, APIs, tables and validation. | Planned | 0% | Day 4
Day 5 | Lesson, session and screen contract | Define exactly what the Author creates and what the LMS stores. | Poojitha | Frontend | Frontend — Define the lesson setup and screen-list fields shown to the Author. | Reviewed lesson/session/screen/object contract for Frontend | UI fields, service commands, existing/new tables, validation, revision handling and permission boundaries agree; implementation follows on Days 6?8. | One reviewed contract covers UI fields, APIs, tables and validation. | Planned | 0% | Day 4
Day 5 | Lesson, session and screen contract | Define exactly what the Author creates and what the LMS stores. | Dhanunjaya | Backend | Backend — Define create, read, update, reorder and validation API contracts. | Reviewed lesson/session/screen/object contract for Backend | UI fields, service commands, existing/new tables, validation, revision handling and permission boundaries agree; implementation follows on Days 6?8. | One reviewed contract covers UI fields, APIs, tables and validation. | Planned | 0% | Day 4
Day 5 | Lesson, session and screen contract | Define exactly what the Author creates and what the LMS stores. | Teja | QA | QA — Write happy-path, invalid-input and permission acceptance cases. | Reviewed lesson/session/screen/object contract for QA | UI fields, service commands, existing/new tables, validation, revision handling and permission boundaries agree; implementation follows on Days 6?8. | One reviewed contract covers UI fields, APIs, tables and validation. | Planned | 0% | Day 4
Day 6 | Studio persistence migration | Validate and extend existing Studio SQL scripts 001?004 against a clean isolated PostgreSQL/Supabase database. | Rahul | Backend | Backend — Add migration execution and service bootstrap needed by Studio. | Working API/service for Studio persistence migration | The service/API works with permissions and error handling and is ready for QA. | Existing SQL plus reviewed changes run from a clean local database; tenant constraints, seed prerequisites and recovery are evidenced. No hosted production writes. | Planned | 0% | Day 5
Day 6 | Studio persistence migration | Validate and extend existing Studio SQL scripts 001?004 against a clean isolated PostgreSQL/Supabase database. | Poojitha | Database | Database ? Reuse and review SQL 001?004; add only missing LMS-aligned persistence changes, with clean migration and integrity checks. | Reviewed schema, migration or data change for Studio persistence migration | The schema/query change runs locally, preserves integrity and is ready for QA. | Existing SQL plus reviewed changes run from a clean local database; tenant constraints, seed prerequisites and recovery are evidenced. No hosted production writes. | Planned | 0% | Day 5
Day 6 | Studio persistence migration | Validate and extend existing Studio SQL scripts 001?004 against a clean isolated PostgreSQL/Supabase database. | Dhanunjaya | Frontend | Frontend — Update frontend types and mock data to match the approved contract. | Working UI/component for Studio persistence migration | The UI works in the agreed flow and is ready for QA. | Existing SQL plus reviewed changes run from a clean local database; tenant constraints, seed prerequisites and recovery are evidenced. No hosted production writes. | Planned | 0% | Day 5
Day 6 | Studio persistence migration | Validate and extend existing Studio SQL scripts 001?004 against a clean isolated PostgreSQL/Supabase database. | Teja | QA | QA — Run the migration repeatedly in local Supabase and verify clean rollback/reset. | Executed test results and defect update for Studio persistence migration | Planned tests are executed, and pass/fail evidence and defects are recorded. | Existing SQL plus reviewed changes run from a clean local database; tenant constraints, seed prerequisites and recovery are evidenced. No hosted production writes. | Planned | 0% | Day 5
Day 7 | Lesson and session APIs | Allow an Author to create and update a scoped lesson and its sessions. | Rahul | Frontend | Frontend — Build the lesson/session setup form and visible validation messages. | Working UI/component for Lesson and session APIs | The UI works in the agreed flow and is ready for QA. | An authorized Author can save and reload a lesson/session; invalid access is rejected. | Planned | 0% | Day 6
Day 7 | Lesson and session APIs | Allow an Author to create and update a scoped lesson and its sessions. | Poojitha | Backend | Backend — Implement scoped lesson and session CRUD services and routes. | Working API/service for Lesson and session APIs | The service/API works with permissions and error handling and is ready for QA. | An authorized Author can save and reload a lesson/session; invalid access is rejected. | Planned | 0% | Day 6
Day 7 | Lesson and session APIs | Allow an Author to create and update a scoped lesson and its sessions. | Dhanunjaya | Database | Database — Implement repository queries, relationships and useful indexes. | Reviewed schema, migration or data change for Lesson and session APIs | The schema/query change runs locally, preserves integrity and is ready for QA. | An authorized Author can save and reload a lesson/session; invalid access is rejected. | Planned | 0% | Day 6
Day 7 | Lesson and session APIs | Allow an Author to create and update a scoped lesson and its sessions. | Teja | QA | QA — Test create, edit, invalid duration, unauthorized access and tenant isolation. | Executed test results and defect update for Lesson and session APIs | Planned tests are executed, and pass/fail evidence and defects are recorded. | An authorized Author can save and reload a lesson/session; invalid access is rejected. | Planned | 0% | Day 6
Day 8 | Screen and object APIs | Save ordered screens and structured objects for a lesson. | Rahul | Database | Database — Implement ordering, object payload and revision persistence. | Reviewed schema, migration or data change for Screen and object APIs | The schema/query change runs locally, preserves integrity and is ready for QA. | Screens and objects round-trip in the correct order with scope checks. | Planned | 0% | Day 7
Day 8 | Screen and object APIs | Save ordered screens and structured objects for a lesson. | Poojitha | Frontend | Frontend — Connect screen creation and object placeholders to API data. | Working UI/component for Screen and object APIs | The UI works in the agreed flow and is ready for QA. | Screens and objects round-trip in the correct order with scope checks. | Planned | 0% | Day 7
Day 8 | Screen and object APIs | Save ordered screens and structured objects for a lesson. | Dhanunjaya | Backend | Backend — Implement screen/object create, edit, delete and reorder endpoints. | Working API/service for Screen and object APIs | The service/API works with permissions and error handling and is ready for QA. | Screens and objects round-trip in the correct order with scope checks. | Planned | 0% | Day 7
Day 8 | Screen and object APIs | Save ordered screens and structured objects for a lesson. | Teja | QA | QA — Test ordering, invalid object types, payload privacy and direct-role denial. | Executed test results and defect update for Screen and object APIs | Planned tests are executed, and pass/fail evidence and defects are recorded. | Screens and objects round-trip in the correct order with scope checks. | Planned | 0% | Day 7
Day 9 | Persisted canvas integration | Display saved lesson screens on the existing canvas. | Rahul | Backend | Backend — Handle save errors, conflicts and stable screen identity. | Working API/service for Persisted canvas integration | The service/API works with permissions and error handling and is ready for QA. | A saved draft screen reloads with the same layout, objects and identity. | Planned | 0% | Day 8
Day 9 | Persisted canvas integration | Display saved lesson screens on the existing canvas. | Poojitha | Database | Database — Create representative local draft data for integration verification. | Reviewed schema, migration or data change for Persisted canvas integration | The schema/query change runs locally, preserves integrity and is ready for QA. | A saved draft screen reloads with the same layout, objects and identity. | Planned | 0% | Day 8
Day 9 | Persisted canvas integration | Display saved lesson screens on the existing canvas. | Dhanunjaya | Frontend | Frontend — Load saved screens into the canvas and save the selected layout. | Working UI/component for Persisted canvas integration | The UI works in the agreed flow and is ready for QA. | A saved draft screen reloads with the same layout, objects and identity. | Planned | 0% | Day 8
Day 9 | Persisted canvas integration | Display saved lesson screens on the existing canvas. | Teja | QA | QA — Verify save, reload, layout retention and error recovery. | Executed test results and defect update for Persisted canvas integration | Planned tests are executed, and pass/fail evidence and defects are recorded. | A saved draft screen reloads with the same layout, objects and identity. | Planned | 0% | Day 8
Day 10 | Foundation integration review | Confirm the LMS integration foundation is stable before Author features expand. | Rahul | Frontend | Frontend — Fix the highest-priority route, form, canvas and responsive issues. | Working UI/component for Foundation integration review | The UI works in the agreed flow and is ready for QA. | The lesson-to-persisted-screen flow passes with no critical open defect. | Planned | 0% | Days 6–9
Day 10 | Foundation integration review | Confirm the LMS integration foundation is stable before Author features expand. | Poojitha | Backend | Backend — Fix the highest-priority API, permission and error-envelope issues. | Working API/service for Foundation integration review | The service/API works with permissions and error handling and is ready for QA. | The lesson-to-persisted-screen flow passes with no critical open defect. | Planned | 0% | Days 6–9
Day 10 | Foundation integration review | Confirm the LMS integration foundation is stable before Author features expand. | Dhanunjaya | Database | Database — Verify migrations, keys, ordering and tenant constraints. | Reviewed schema, migration or data change for Foundation integration review | The schema/query change runs locally, preserves integrity and is ready for QA. | The lesson-to-persisted-screen flow passes with no critical open defect. | Planned | 0% | Days 6–9
Day 10 | Foundation integration review | Confirm the LMS integration foundation is stable before Author features expand. | Teja | QA | QA — Run the Sprint 1 regression and record pass/fail evidence. | Executed test results and defect update for Foundation integration review | Planned tests are executed, and pass/fail evidence and defects are recorded. | The lesson-to-persisted-screen flow passes with no critical open defect. | Planned | 0% | Days 6–9
Day 11 | Structured screen-object editor | Let Authors edit supported teaching objects without a free-form slide clone. | Rahul | Database | Database — Finalize object-type payload storage and revision fields. | Reviewed schema, migration or data change for Structured screen-object editor | The schema/query change runs locally, preserves integrity and is ready for QA. | An Author can create and edit each MVP object type with clear validation. | Planned | 0% | Day 10
Day 11 | Structured screen-object editor | Let Authors edit supported teaching objects without a free-form slide clone. | Poojitha | Frontend | Frontend — Build editing controls for text, visual, question and resource placeholders. | Working UI/component for Structured screen-object editor | The UI works in the agreed flow and is ready for QA. | An Author can create and edit each MVP object type with clear validation. | Planned | 0% | Day 10
Day 11 | Structured screen-object editor | Let Authors edit supported teaching objects without a free-form slide clone. | Dhanunjaya | Backend | Backend — Implement typed object commands and server validation. | Working API/service for Structured screen-object editor | The service/API works with permissions and error handling and is ready for QA. | An Author can create and edit each MVP object type with clear validation. | Planned | 0% | Day 10
Day 11 | Structured screen-object editor | Let Authors edit supported teaching objects without a free-form slide clone. | Teja | QA | QA — Test create/edit for every supported object type and invalid payload handling. | Executed test results and defect update for Structured screen-object editor | Planned tests are executed, and pass/fail evidence and defects are recorded. | An Author can create and edit each MVP object type with clear validation. | Planned | 0% | Day 10
Day 12 | Object save, reorder and validation | Make object changes safe, ordered and understandable. | Rahul | Backend | Backend — Implement transactional save, reorder and conflict handling. | Working API/service for Object save, reorder and validation | The service/API works with permissions and error handling and is ready for QA. | Valid changes save atomically and invalid/conflicting changes do not damage the draft. | Planned | 0% | Day 11
Day 12 | Object save, reorder and validation | Make object changes safe, ordered and understandable. | Poojitha | Database | Database — Enforce stable order and revision/concurrency rules. | Reviewed schema, migration or data change for Object save, reorder and validation | The schema/query change runs locally, preserves integrity and is ready for QA. | Valid changes save atomically and invalid/conflicting changes do not damage the draft. | Planned | 0% | Day 11
Day 12 | Object save, reorder and validation | Make object changes safe, ordered and understandable. | Dhanunjaya | Frontend | Frontend — Add object reorder controls, unsaved-state cues and validation messages. | Working UI/component for Object save, reorder and validation | The UI works in the agreed flow and is ready for QA. | Valid changes save atomically and invalid/conflicting changes do not damage the draft. | Planned | 0% | Day 11
Day 12 | Object save, reorder and validation | Make object changes safe, ordered and understandable. | Teja | QA | QA — Test reorder, partial failure, stale revision and unrelated-object preservation. | Executed test results and defect update for Object save, reorder and validation | Planned tests are executed, and pass/fail evidence and defects are recorded. | Valid changes save atomically and invalid/conflicting changes do not damage the draft. | Planned | 0% | Day 11
Day 13 | Layout switching and reveal behavior | Allow layout changes while preserving compatible content and teaching sequence. | Rahul | Frontend | Frontend — Build layout switching, mapping prompts and basic reveal-step controls. | Working UI/component for Layout switching and reveal behavior | The UI works in the agreed flow and is ready for QA. | Layout changes never silently delete content and reveal state behaves predictably. | Planned | 0% | Day 12
Day 13 | Layout switching and reveal behavior | Allow layout changes while preserving compatible content and teaching sequence. | Poojitha | Backend | Backend — Validate object compatibility and reveal-step commands. | Working API/service for Layout switching and reveal behavior | The service/API works with permissions and error handling and is ready for QA. | Layout changes never silently delete content and reveal state behaves predictably. | Planned | 0% | Day 12
Day 13 | Layout switching and reveal behavior | Allow layout changes while preserving compatible content and teaching sequence. | Dhanunjaya | Database | Database — Persist layout choice, object-slot mapping and reveal order. | Reviewed schema, migration or data change for Layout switching and reveal behavior | The schema/query change runs locally, preserves integrity and is ready for QA. | Layout changes never silently delete content and reveal state behaves predictably. | Planned | 0% | Day 12
Day 13 | Layout switching and reveal behavior | Allow layout changes while preserving compatible content and teaching sequence. | Teja | QA | QA — Test compatible switches, incompatible warnings and reveal forward/reverse behavior. | Executed test results and defect update for Layout switching and reveal behavior | Planned tests are executed, and pass/fail evidence and defects are recorded. | Layout changes never silently delete content and reveal state behaves predictably. | Planned | 0% | Day 12
Day 14 | Resource intake foundation | Let Authors add a native item, file, external link or existing LMS resource. | Rahul | Database | Database — Implement resource item/version records aligned to the LMS tenant model. | Reviewed schema, migration or data change for Resource intake foundation | The schema/query change runs locally, preserves integrity and is ready for QA. | Create native text/simple quiz, upload agreed image/PDF formats, add reviewed HTTPS link and map internal resource as recoverable candidates. Unsupported formats are rejected with recovery. Executable HTML/ZIP, provider embeds and SCORM execution are deferred. | Planned | 0% | Days 4 and 10
Day 14 | Resource intake foundation | Let Authors add a native item, file, external link or existing LMS resource. | Poojitha | Frontend | Frontend — Build a single Add Resource flow with the four MVP entry routes. | Working UI/component for Resource intake foundation | The UI works in the agreed flow and is ready for QA. | Create native text/simple quiz, upload agreed image/PDF formats, add reviewed HTTPS link and map internal resource as recoverable candidates. Unsupported formats are rejected with recovery. Executable HTML/ZIP, provider embeds and SCORM execution are deferred. | Planned | 0% | Days 4 and 10
Day 14 | Resource intake foundation | Let Authors add a native item, file, external link or existing LMS resource. | Dhanunjaya | Backend | Backend — Implement create, upload, link and internal-map commands with validation. | Working API/service for Resource intake foundation | The service/API works with permissions and error handling and is ready for QA. | Create native text/simple quiz, upload agreed image/PDF formats, add reviewed HTTPS link and map internal resource as recoverable candidates. Unsupported formats are rejected with recovery. Executable HTML/ZIP, provider embeds and SCORM execution are deferred. | Planned | 0% | Days 4 and 10
Day 14 | Resource intake foundation | Let Authors add a native item, file, external link or existing LMS resource. | Teja | QA | QA — Test every route, unsupported format, interrupted upload and recovery message. | Executed test results and defect update for Resource intake foundation | Planned tests are executed, and pass/fail evidence and defects are recorded. | Create native text/simple quiz, upload agreed image/PDF formats, add reviewed HTTPS link and map internal resource as recoverable candidates. Unsupported formats are rejected with recovery. Executable HTML/ZIP, provider embeds and SCORM execution are deferred. | Planned | 0% | Days 4 and 10
Day 15 | Resource version and academic review | Protect approved resource versions and record review decisions. | Rahul | Backend | Backend — Implement candidate, approve, reject and withdraw transitions. | Working API/service for Resource version and academic review | The service/API works with permissions and error handling and is ready for QA. | Scoped Author review identifies exact content hash, rationale, rights/accessibility and fallback. Approved payloads are immutable; withdrawal blocks new use while retaining references. | Planned | 0% | Day 14
Day 15 | Resource version and academic review | Protect approved resource versions and record review decisions. | Poojitha | Database | Database — Enforce version numbering, immutable approved payloads and append-only decisions. | Reviewed schema, migration or data change for Resource version and academic review | The schema/query change runs locally, preserves integrity and is ready for QA. | Scoped Author review identifies exact content hash, rationale, rights/accessibility and fallback. Approved payloads are immutable; withdrawal blocks new use while retaining references. | Planned | 0% | Day 14
Day 15 | Resource version and academic review | Protect approved resource versions and record review decisions. | Dhanunjaya | Frontend | Frontend — Build candidate-version, review-status and decision views. | Working UI/component for Resource version and academic review | The UI works in the agreed flow and is ready for QA. | Scoped Author review identifies exact content hash, rationale, rights/accessibility and fallback. Approved payloads are immutable; withdrawal blocks new use while retaining references. | Planned | 0% | Day 14
Day 15 | Resource version and academic review | Protect approved resource versions and record review decisions. | Teja | QA | QA — Test allowed transitions, mutation rejection and referenced-version protection. | Executed test results and defect update for Resource version and academic review | Planned tests are executed, and pass/fail evidence and defects are recorded. | Scoped Author review identifies exact content hash, rationale, rights/accessibility and fallback. Approved payloads are immutable; withdrawal blocks new use while retaining references. | Planned | 0% | Day 14
Day 16 | Resource Library search and filters | Help Authors find reusable approved resources quickly. | Rahul | Frontend | Frontend — Build catalog, search, type/subject/grade filters and pagination. | Working UI/component for Resource Library search and filters | The UI works in the agreed flow and is ready for QA. | Authorized users can find approved resources using combined filters without scope leakage. | Planned | 0% | Day 15
Day 16 | Resource Library search and filters | Help Authors find reusable approved resources quickly. | Poojitha | Backend | Backend — Implement scoped search and filter APIs. | Working API/service for Resource Library search and filters | The service/API works with permissions and error handling and is ready for QA. | Authorized users can find approved resources using combined filters without scope leakage. | Planned | 0% | Day 15
Day 16 | Resource Library search and filters | Help Authors find reusable approved resources quickly. | Dhanunjaya | Database | Database — Add academic mappings and indexes required by catalog queries. | Reviewed schema, migration or data change for Resource Library search and filters | The schema/query change runs locally, preserves integrity and is ready for QA. | Authorized users can find approved resources using combined filters without scope leakage. | Planned | 0% | Day 15
Day 16 | Resource Library search and filters | Help Authors find reusable approved resources quickly. | Teja | QA | QA — Test combined filters, pagination, empty results and tenant/role boundaries. | Executed test results and defect update for Resource Library search and filters | Planned tests are executed, and pass/fail evidence and defects are recorded. | Authorized users can find approved resources using combined filters without scope leakage. | Planned | 0% | Day 15
Day 17 | Exact-version resource binding | Attach one approved version to a screen with context-specific instructions. | Rahul | Database | Database — Enforce exact version, one placement owner and independent binding data. | Reviewed schema, migration or data change for Exact-version resource binding | The schema/query change runs locally, preserves integrity and is ready for QA. | One approved version is reused across two lessons, preferably two subjects, without duplicate bytes; each binding keeps independent prompts, audience, launch settings and fallback. | Planned | 0% | Day 16
Day 17 | Exact-version resource binding | Attach one approved version to a screen with context-specific instructions. | Poojitha | Frontend | Frontend — Build attach-resource and placement-instructions controls. | Working UI/component for Exact-version resource binding | The UI works in the agreed flow and is ready for QA. | One approved version is reused across two lessons, preferably two subjects, without duplicate bytes; each binding keeps independent prompts, audience, launch settings and fallback. | Planned | 0% | Day 16
Day 17 | Exact-version resource binding | Attach one approved version to a screen with context-specific instructions. | Dhanunjaya | Backend | Backend — Implement binding creation and approved-version validation. | Working API/service for Exact-version resource binding | The service/API works with permissions and error handling and is ready for QA. | One approved version is reused across two lessons, preferably two subjects, without duplicate bytes; each binding keeps independent prompts, audience, launch settings and fallback. | Planned | 0% | Day 16
Day 17 | Exact-version resource binding | Attach one approved version to a screen with context-specific instructions. | Teja | QA | QA — Test one version reused in two lessons with different prompts and fallbacks. | Executed test results and defect update for Exact-version resource binding | Planned tests are executed, and pass/fail evidence and defects are recorded. | One approved version is reused across two lessons, preferably two subjects, without duplicate bytes; each binding keeps independent prompts, audience, launch settings and fallback. | Planned | 0% | Day 16
Day 18 | Clarification branch and return state | Let a Teacher open one clarification and return to the exact lesson position. | Rahul | Backend | Backend — Implement branch launch and screen-state restoration services. | Working API/service for Clarification branch and return state | The service/API works with permissions and error handling and is ready for QA. | Teacher branch preview returns to the same screen, reveal and supported interaction state; persisted run verification is repeated on Day 23. Learner payload omits private branches. | Planned | 0% | Day 17; preview harness only until Day 23 release player
Day 18 | Clarification branch and return state | Let a Teacher open one clarification and return to the exact lesson position. | Poojitha | Database | Database — Persist branch ownership, resource binding and return-state reference. | Reviewed schema, migration or data change for Clarification branch and return state | The schema/query change runs locally, preserves integrity and is ready for QA. | Teacher branch preview returns to the same screen, reveal and supported interaction state; persisted run verification is repeated on Day 23. Learner payload omits private branches. | Planned | 0% | Day 17; preview harness only until Day 23 release player
Day 18 | Clarification branch and return state | Let a Teacher open one clarification and return to the exact lesson position. | Dhanunjaya | Frontend | Frontend — Build branch entry, branch view and Return controls. | Working UI/component for Clarification branch and return state | The UI works in the agreed flow and is ready for QA. | Teacher branch preview returns to the same screen, reveal and supported interaction state; persisted run verification is repeated on Day 23. Learner payload omits private branches. | Planned | 0% | Day 17; preview harness only until Day 23 release player
Day 18 | Clarification branch and return state | Let a Teacher open one clarification and return to the exact lesson position. | Teja | QA | QA — Test entry, interaction, return, reveal-position retention and failure recovery. | Executed test results and defect update for Clarification branch and return state | Planned tests are executed, and pass/fail evidence and defects are recorded. | Teacher branch preview returns to the same screen, reveal and supported interaction state; persisted run verification is repeated on Day 23. Learner payload omits private branches. | Planned | 0% | Day 17; preview harness only until Day 23 release player
Day 19 | Security and accessibility hardening | Protect private fields and make the MVP usable with keyboard and classroom projection. | Rahul | Frontend | Frontend — Fix keyboard flow, labels, contrast, focus and projection readability. | Working UI/component for Security and accessibility hardening | The UI works in the agreed flow and is ready for QA. | Signed-in Author/Teacher/Student cases verify client/school/scope restrictions, direct API and asset denial, private metadata omission, keyboard/focus and projection readability; no critical blocker remains. | Planned | 0% | Days 11–18 | Access checks start on Day 3 and apply to every API from first implementation; Day 19 consolidates hardening, not first security implementation.
Day 19 | Security and accessibility hardening | Protect private fields and make the MVP usable with keyboard and classroom projection. | Poojitha | Backend | Backend — Implement learner-safe/teacher-safe response projections and denial handling. | Working API/service for Security and accessibility hardening | The service/API works with permissions and error handling and is ready for QA. | Signed-in Author/Teacher/Student cases verify client/school/scope restrictions, direct API and asset denial, private metadata omission, keyboard/focus and projection readability; no critical blocker remains. | Planned | 0% | Days 11–18 | Access checks start on Day 3 and apply to every API from first implementation; Day 19 consolidates hardening, not first security implementation.
Day 19 | Security and accessibility hardening | Protect private fields and make the MVP usable with keyboard and classroom projection. | Dhanunjaya | Database | Database — Review tenant constraints and RLS/grant expectations for Studio tables. | Reviewed schema, migration or data change for Security and accessibility hardening | The schema/query change runs locally, preserves integrity and is ready for QA. | Signed-in Author/Teacher/Student cases verify client/school/scope restrictions, direct API and asset denial, private metadata omission, keyboard/focus and projection readability; no critical blocker remains. | Planned | 0% | Days 11–18 | Access checks start on Day 3 and apply to every API from first implementation; Day 19 consolidates hardening, not first security implementation.
Day 19 | Security and accessibility hardening | Protect private fields and make the MVP usable with keyboard and classroom projection. | Teja | QA | QA — Run permission, payload-leak, keyboard, contrast and responsive checks. | Executed test results and defect update for Security and accessibility hardening | Planned tests are executed, and pass/fail evidence and defects are recorded. | Signed-in Author/Teacher/Student cases verify client/school/scope restrictions, direct API and asset denial, private metadata omission, keyboard/focus and projection readability; no critical blocker remains. | Planned | 0% | Days 11–18 | Access checks start on Day 3 and apply to every API from first implementation; Day 19 consolidates hardening, not first security implementation.
Day 20 | Author MVP review | Prove the Author can build a screen and reuse an approved resource end to end. | Rahul | Database | Database — Verify saved draft, version and binding data for the scenario. | Reviewed schema, migration or data change for Author MVP review | The schema/query change runs locally, preserves integrity and is ready for QA. | Author creates, saves, reloads and previews a screen with an approved exact-version resource; validation findings and draft status are visible. This is an authoring gate, not production release approval. | Planned | 0% | Days 11–19
Day 20 | Author MVP review | Prove the Author can build a screen and reuse an approved resource end to end. | Poojitha | Frontend | Frontend — Complete the Author journey and fix usability blockers. | Working UI/component for Author MVP review | The UI works in the agreed flow and is ready for QA. | Author creates, saves, reloads and previews a screen with an approved exact-version resource; validation findings and draft status are visible. This is an authoring gate, not production release approval. | Planned | 0% | Days 11–19
Day 20 | Author MVP review | Prove the Author can build a screen and reuse an approved resource end to end. | Dhanunjaya | Backend | Backend — Complete end-to-end orchestration and fix API blockers. | Working API/service for Author MVP review | The service/API works with permissions and error handling and is ready for QA. | Author creates, saves, reloads and previews a screen with an approved exact-version resource; validation findings and draft status are visible. This is an authoring gate, not production release approval. | Planned | 0% | Days 11–19
Day 20 | Author MVP review | Prove the Author can build a screen and reuse an approved resource end to end. | Teja | QA | QA — Run the Author acceptance scenario and record defects/evidence. | Executed test results and defect update for Author MVP review | Planned tests are executed, and pass/fail evidence and defects are recorded. | Author creates, saves, reloads and previews a screen with an approved exact-version resource; validation findings and draft status are visible. This is an authoring gate, not production release approval. | Planned | 0% | Days 11–19
Day 21 | Academic authorization workflow | Record who authorizes which exact lesson revision and scope. | Rahul | Backend | Backend — Implement authorization command, permissions and rejection handling. | Working API/service for Academic authorization workflow | The service/API works with permissions and error handling and is ready for QA. | Only a scoped permitted Author can approve an exact validated lesson revision/hash; record rationale, timestamp and validator version. Changes invalidate prior approval for the changed revision. | Planned | 0% | Day 20
Day 21 | Academic authorization workflow | Record who authorizes which exact lesson revision and scope. | Poojitha | Database | Database — Persist authorizer, exact revision, scope, decision and timestamp. | Reviewed schema, migration or data change for Academic authorization workflow | The schema/query change runs locally, preserves integrity and is ready for QA. | Only a scoped permitted Author can approve an exact validated lesson revision/hash; record rationale, timestamp and validator version. Changes invalidate prior approval for the changed revision. | Planned | 0% | Day 20
Day 21 | Academic authorization workflow | Record who authorizes which exact lesson revision and scope. | Dhanunjaya | Frontend | Frontend — Build review summary, authorize/reject action and reason display. | Working UI/component for Academic authorization workflow | The UI works in the agreed flow and is ready for QA. | Only a scoped permitted Author can approve an exact validated lesson revision/hash; record rationale, timestamp and validator version. Changes invalidate prior approval for the changed revision. | Planned | 0% | Day 20
Day 21 | Academic authorization workflow | Record who authorizes which exact lesson revision and scope. | Teja | QA | QA — Test permitted authorizer, denied roles, rejection and changed-draft reauthorization. | Executed test results and defect update for Academic authorization workflow | Planned tests are executed, and pass/fail evidence and defects are recorded. | Only a scoped permitted Author can approve an exact validated lesson revision/hash; record rationale, timestamp and validator version. Changes invalidate prior approval for the changed revision. | Planned | 0% | Day 20
Day 22 | Immutable release manifest | Publish a release that pins exact lesson and resource versions. | Rahul | Frontend | Frontend — Build release-readiness summary and published-version display. | Working UI/component for Immutable release manifest | The UI works in the agreed flow and is ready for QA. | Only authorized validated content publishes. Immutable manifest pins screen, binding, resource and dependency versions/hashes; concurrent draft changes cannot alter it. | Planned | 0% | Day 21
Day 22 | Immutable release manifest | Publish a release that pins exact lesson and resource versions. | Poojitha | Backend | Backend — Generate deterministic release manifest and block unapproved publication. | Working API/service for Immutable release manifest | The service/API works with permissions and error handling and is ready for QA. | Only authorized validated content publishes. Immutable manifest pins screen, binding, resource and dependency versions/hashes; concurrent draft changes cannot alter it. | Planned | 0% | Day 21
Day 22 | Immutable release manifest | Publish a release that pins exact lesson and resource versions. | Dhanunjaya | Database | Database — Persist immutable release and exact release items/hashes. | Reviewed schema, migration or data change for Immutable release manifest | The schema/query change runs locally, preserves integrity and is ready for QA. | Only authorized validated content publishes. Immutable manifest pins screen, binding, resource and dependency versions/hashes; concurrent draft changes cannot alter it. | Planned | 0% | Day 21
Day 22 | Immutable release manifest | Publish a release that pins exact lesson and resource versions. | Teja | QA | QA — Test publication, changed draft, manifest stability and rollback selection. | Executed test results and defect update for Immutable release manifest | Planned tests are executed, and pass/fail evidence and defects are recorded. | Only authorized validated content publishes. Immutable manifest pins screen, binding, resource and dependency versions/hashes; concurrent draft changes cannot alter it. | Planned | 0% | Day 21
Day 23 | Teacher read-only release player | Let a Teacher launch the approved release without editing canonical content. | Rahul | Database | Database — Record release selection and minimal teaching-run identity. | Reviewed schema, migration or data change for Teacher read-only release player | The schema/query change runs locally, preserves integrity and is ready for QA. | Teacher launches an approved release pinned to a scoped teaching run; student-safe projection excludes private catalog/notes/keys. Branch return and publication during a live run preserve state; canonical writes are denied. | Planned | 0% | Day 22 | Student role privacy is mandatory in MVP. Durable response analytics and feedback work queues are follow-up scope.
Day 23 | Teacher read-only release player | Let a Teacher launch the approved release without editing canonical content. | Poojitha | Frontend | Frontend — Build Teacher player navigation, notes boundary and branch access. | Working UI/component for Teacher read-only release player | The UI works in the agreed flow and is ready for QA. | Teacher launches an approved release pinned to a scoped teaching run; student-safe projection excludes private catalog/notes/keys. Branch return and publication during a live run preserve state; canonical writes are denied. | Planned | 0% | Day 22 | Student role privacy is mandatory in MVP. Durable response analytics and feedback work queues are follow-up scope.
Day 23 | Teacher read-only release player | Let a Teacher launch the approved release without editing canonical content. | Dhanunjaya | Backend | Backend — Serve release-pinned Teacher projections and block canonical writes. | Working API/service for Teacher read-only release player | The service/API works with permissions and error handling and is ready for QA. | Teacher launches an approved release pinned to a scoped teaching run; student-safe projection excludes private catalog/notes/keys. Branch return and publication during a live run preserve state; canonical writes are denied. | Planned | 0% | Day 22 | Student role privacy is mandatory in MVP. Durable response analytics and feedback work queues are follow-up scope.
Day 23 | Teacher read-only release player | Let a Teacher launch the approved release without editing canonical content. | Teja | QA | QA — Test approved launch, denied draft launch, direct write denial and branch return. | Executed test results and defect update for Teacher read-only release player | Planned tests are executed, and pass/fail evidence and defects are recorded. | Teacher launches an approved release pinned to a scoped teaching run; student-safe projection excludes private catalog/notes/keys. Branch return and publication during a live run preserve state; canonical writes are denied. | Planned | 0% | Day 22 | Student role privacy is mandatory in MVP. Durable response analytics and feedback work queues are follow-up scope.
Day 24 | Representative pilot lesson migration | Move one reviewed pilot lesson slice into governed Studio drafts. | Rahul | Backend | Backend — Build the repeatable migration/import command for the selected slice. | Working API/service for Representative pilot lesson migration | The service/API works with permissions and error handling and is ready for QA. | An available reviewed source slice imports as a draft with provenance, content/order/resource comparison and unsupported-item report. If pilot source is unavailable, use an explicitly labeled reviewed fixture; do not claim 523 branches migrated. | Planned | 0% | Days 17 and 22; source access/inventory confirmed on Day 1
Day 24 | Representative pilot lesson migration | Move one reviewed pilot lesson slice into governed Studio drafts. | Poojitha | Database | Database — Map source IDs to lesson, screen, resource and binding records. | Reviewed schema, migration or data change for Representative pilot lesson migration | The schema/query change runs locally, preserves integrity and is ready for QA. | An available reviewed source slice imports as a draft with provenance, content/order/resource comparison and unsupported-item report. If pilot source is unavailable, use an explicitly labeled reviewed fixture; do not claim 523 branches migrated. | Planned | 0% | Days 17 and 22; source access/inventory confirmed on Day 1
Day 24 | Representative pilot lesson migration | Move one reviewed pilot lesson slice into governed Studio drafts. | Dhanunjaya | Frontend | Frontend — Review migrated screens and map unsupported visual/layout items. | Working UI/component for Representative pilot lesson migration | The UI works in the agreed flow and is ready for QA. | An available reviewed source slice imports as a draft with provenance, content/order/resource comparison and unsupported-item report. If pilot source is unavailable, use an explicitly labeled reviewed fixture; do not claim 523 branches migrated. | Planned | 0% | Days 17 and 22; source access/inventory confirmed on Day 1
Day 24 | Representative pilot lesson migration | Move one reviewed pilot lesson slice into governed Studio drafts. | Teja | QA | QA — Compare migrated content, order, mappings and role visibility with the source. | Executed test results and defect update for Representative pilot lesson migration | Planned tests are executed, and pass/fail evidence and defects are recorded. | An available reviewed source slice imports as a draft with provenance, content/order/resource comparison and unsupported-item report. If pilot source is unavailable, use an explicitly labeled reviewed fixture; do not claim 523 branches migrated. | Planned | 0% | Days 17 and 22; source access/inventory confirmed on Day 1
Day 25 | End-to-end regression and blocker fixes | Stabilize the complete Author-to-Teacher MVP path. | Rahul | Frontend | Frontend — Fix critical UI defects found in end-to-end testing. | Working UI/component for End-to-end regression and blocker fixes | The UI works in the agreed flow and is ready for QA. | Author?validate?authorize?publish?Teacher run?student-safe projection passes; stale saves, draft denial, failed media fallback, exact-version reuse and unchanged live release are evidenced. Existing LMS login/curriculum/course/exam/teaching-session smoke checks pass. | Planned | 0% | Days 20–24
Day 25 | End-to-end regression and blocker fixes | Stabilize the complete Author-to-Teacher MVP path. | Poojitha | Backend | Backend — Fix critical service, permission and error-handling defects. | Working API/service for End-to-end regression and blocker fixes | The service/API works with permissions and error handling and is ready for QA. | Author?validate?authorize?publish?Teacher run?student-safe projection passes; stale saves, draft denial, failed media fallback, exact-version reuse and unchanged live release are evidenced. Existing LMS login/curriculum/course/exam/teaching-session smoke checks pass. | Planned | 0% | Days 20–24
Day 25 | End-to-end regression and blocker fixes | Stabilize the complete Author-to-Teacher MVP path. | Dhanunjaya | Database | Database — Fix critical migration, data-integrity and query defects. | Reviewed schema, migration or data change for End-to-end regression and blocker fixes | The schema/query change runs locally, preserves integrity and is ready for QA. | Author?validate?authorize?publish?Teacher run?student-safe projection passes; stale saves, draft denial, failed media fallback, exact-version reuse and unchanged live release are evidenced. Existing LMS login/curriculum/course/exam/teaching-session smoke checks pass. | Planned | 0% | Days 20–24
Day 25 | End-to-end regression and blocker fixes | Stabilize the complete Author-to-Teacher MVP path. | Teja | QA | QA — Run full MVP regression and separate existing LMS defects from Studio defects. | Executed test results and defect update for End-to-end regression and blocker fixes | Planned tests are executed, and pass/fail evidence and defects are recorded. | Author?validate?authorize?publish?Teacher run?student-safe projection passes; stale saves, draft denial, failed media fallback, exact-version reuse and unchanged live release are evidenced. Existing LMS login/curriculum/course/exam/teaching-session smoke checks pass. | Planned | 0% | Days 20–24
Day 26 | Documentation and team operating guide | Give the team and users clear instructions that match the implemented system. | Rahul | Database | Database — Document schema, migrations, backup and recovery steps. | Reviewed Database runbook and handover documentation | Documented commands and flows match the build, distinguish supported/deferred capabilities, and include owners, known limitations and recovery steps. | A new team member can run and verify the MVP using the documented steps. | Planned | 0% | Day 25
Day 26 | Documentation and team operating guide | Give the team and users clear instructions that match the implemented system. | Poojitha | Frontend | Frontend — Document Author and Teacher UI steps with current screenshots/labels. | Reviewed Frontend runbook and handover documentation | Documented commands and flows match the build, distinguish supported/deferred capabilities, and include owners, known limitations and recovery steps. | A new team member can run and verify the MVP using the documented steps. | Planned | 0% | Day 25
Day 26 | Documentation and team operating guide | Give the team and users clear instructions that match the implemented system. | Dhanunjaya | Backend | Backend — Document APIs, permissions, errors and local run steps. | Reviewed Backend runbook and handover documentation | Documented commands and flows match the build, distinguish supported/deferred capabilities, and include owners, known limitations and recovery steps. | A new team member can run and verify the MVP using the documented steps. | Planned | 0% | Day 25
Day 26 | Documentation and team operating guide | Give the team and users clear instructions that match the implemented system. | Teja | QA | QA — Review every instruction against the build and record mismatches. | Reviewed QA runbook and handover documentation | Documented commands and flows match the build, distinguish supported/deferred capabilities, and include owners, known limitations and recovery steps. | A new team member can run and verify the MVP using the documented steps. | Planned | 0% | Day 25
Day 27 | Staging deployment and user acceptance | Verify the MVP in a staging-like environment with representative users. | Rahul | Backend | Backend — Deploy APIs, configuration and health checks; prepare rollback. | Working API/service for Staging deployment and user acceptance | The service/API works with permissions and error handling and is ready for QA. | Representative signed-in roles pass staging UAT; database AND referenced asset versions restore with integrity checked, rollback is exercised, and measured recovery results are recorded. Production remains gated on Day 28. | Planned | 0% | Days 25–26
Day 27 | Staging deployment and user acceptance | Verify the MVP in a staging-like environment with representative users. | Poojitha | Database | Database — Apply reviewed migrations and verify backup/restore in staging. | Reviewed schema, migration or data change for Staging deployment and user acceptance | The schema/query change runs locally, preserves integrity and is ready for QA. | Representative signed-in roles pass staging UAT; database AND referenced asset versions restore with integrity checked, rollback is exercised, and measured recovery results are recorded. Production remains gated on Day 28. | Planned | 0% | Days 25–26
Day 27 | Staging deployment and user acceptance | Verify the MVP in a staging-like environment with representative users. | Dhanunjaya | Frontend | Frontend — Deploy and verify the user flows and projection layout in staging. | Working UI/component for Staging deployment and user acceptance | The UI works in the agreed flow and is ready for QA. | Representative signed-in roles pass staging UAT; database AND referenced asset versions restore with integrity checked, rollback is exercised, and measured recovery results are recorded. Production remains gated on Day 28. | Planned | 0% | Days 25–26
Day 27 | Staging deployment and user acceptance | Verify the MVP in a staging-like environment with representative users. | Teja | QA | QA — Run Author and Teacher UAT scenarios and record acceptance/blockers. | Executed test results and defect update for Staging deployment and user acceptance | Planned tests are executed, and pass/fail evidence and defects are recorded. | Representative signed-in roles pass staging UAT; database AND referenced asset versions restore with integrity checked, rollback is exercised, and measured recovery results are recorded. Production remains gated on Day 28. | Planned | 0% | Days 25–26
Day 28 | Release decision and handover | Make a clear go/no-go decision and hand over the accepted MVP. | Rahul | Frontend | Frontend — Close approved UI issues and demonstrate the final user flow. | Working UI/component for Release decision and handover | The UI works in the agreed flow and is ready for QA. | Record go/no-go against Scope and Gates, academic/content authorization, QA evidence, operational ownership and accepted limitations. Production release occurs only after named release-owner approval; failed gates extend the plan. | Planned | 0% | Day 27
Day 28 | Release decision and handover | Make a clear go/no-go decision and hand over the accepted MVP. | Poojitha | Backend | Backend — Confirm services, monitoring, configuration and rollback ownership. | Working API/service for Release decision and handover | The service/API works with permissions and error handling and is ready for QA. | Record go/no-go against Scope and Gates, academic/content authorization, QA evidence, operational ownership and accepted limitations. Production release occurs only after named release-owner approval; failed gates extend the plan. | Planned | 0% | Day 27
Day 28 | Release decision and handover | Make a clear go/no-go decision and hand over the accepted MVP. | Dhanunjaya | Database | Database — Confirm migration status, backup evidence and recovery ownership. | Reviewed schema, migration or data change for Release decision and handover | The schema/query change runs locally, preserves integrity and is ready for QA. | Record go/no-go against Scope and Gates, academic/content authorization, QA evidence, operational ownership and accepted limitations. Production release occurs only after named release-owner approval; failed gates extend the plan. | Planned | 0% | Day 27
Day 28 | Release decision and handover | Make a clear go/no-go decision and hand over the accepted MVP. | Teja | QA | QA — Present the final quality summary, open issues and release recommendation. | Executed test results and defect update for Release decision and handover | Planned tests are executed, and pass/fail evidence and defects are recorded. | Record go/no-go against Scope and Gates, academic/content authorization, QA evidence, operational ownership and accepted limitations. Production release occurs only after named release-owner approval; failed gates extend the plan. | Planned | 0% | Day 27

## Scope and Gates
Topic | Corrected planning rule | Acceptance / evidence
Purpose | Deliver an initial governed authoring, resource reuse and classroom delivery MVP in 28 provisional working days. | This workbook is a plan, not evidence of completed functionality or a guarantee of duration.
Existing stack | React 19/Vite/TypeScript; Express/Node; PostgreSQL/Supabase; existing LMS JWT auth, permissions and entitlements. | Reuse repository services; no Cloudflare Worker/D1 platform migration is included.
Existing data | Review Studio SQL 001?004 rather than create duplicate parallel models. Existing SQL uses client_id, school_id, integer LMS user and academic references; Studio entities use UUIDs. | Inspect constraints, applied migration state and data in an isolated environment. SQL files do not prove live database deployment.
Authority | Map content_authorizer and other permitted LMS roles to explicitly scoped Studio commands. Platform ownership is not academic authorization. | Reviewed role/scope/entitlement matrix, denied-write tests and same-tenant relationships.
MVP authoring | Lesson/session/screen drafts; structured text, visual, question and resource objects; saved ordering; supported layouts; basic reveals; conflict handling. | Save/reload and unrelated-content preservation tests. Scope supported object/layout types before build.
MVP resource routes | Native text/simple quiz; agreed image/PDF upload; reviewed HTTPS link; internal-map reuse. | Declare exact formats, limits, rights, accessibility, fallback and preview behavior. Arbitrary source projects and conversation URLs are not executable content.
MVP library | Items, exact versions, scoped academic mappings, search/type/subject/grade filters, pagination, review, bindings, referenced-version protection and withdrawal. | One exact approved version in two lessons with independent teaching context; no silent replacement.
MVP release and delivery | Validate exact revision, academic approval, immutable pinned release, Teacher run, branch return, student-safe projection. | Any later draft/resource candidate leaves active releases and runs unchanged.
Mandatory privacy | Apply permissions from the first route. Hide private data server-side, including assets and metadata. Student-safe payload checks remain in scope. | Real signed-in role tests plus direct API/file denial and cross-client/school/scope tests.
Status integrity | Days 1?3 changed from Complete to Needs verification; old evidence references retained as unverified claims. | Attach repository revision, actual path/report, executed commands/results and reviewer before setting Complete.
Integration gate | Day 4 confirms the mapping already represented in SQL and resolves gaps. Do not design a second tenant or curriculum system. | Approved adapter and migration contract before persisted feature work.
Prototype versus production | Day 18 branch work uses a preview harness. Day 23 repeats branch behavior against approved release-pinned teaching runs. | A preview does not constitute authorized classroom publication.
Pilot migration | Inventory actual accessible pilot sources on Day 1; migrate one reviewed representative slice on Day 24. | If sources are unavailable use a labeled fixture and record the limitation. Never claim all 523 branches migrated without comparison evidence.
Estimate and capacity | 28 working days excluding holidays is a sequencing target. Estimate each assignment with the named owner at kickoff; include integration, review and defect time. | Reforecast at Days 4, 10, 20 and 25. Unmet gates extend the schedule; do not drop required checks to meet Day 28.
Team ownership | Preserve named assignees and rotating roles in the source tracker as provisional. Confirm skills/capacity and reviewer at kickoff. | Each task has one accountable owner; QA executes against usable builds, records blockers and retests fixes.
Same-day dependencies | Database/API/UI/QA entries describe shared daily goals; they are not assumed to finish simultaneously. Agree contracts first, then integrate and test. | Use mocks/contracts where safe; carry incomplete dependent work forward and adjust forecast.
Completion evidence | Schedule column M records commit, report path, tested environment, command/results, reviewer and accepted limitations. | Complete requires both individual acceptance and the shared daily gate. Keep status and progress synchronized.
Recovery | Back up and restore relational data plus referenced immutable asset versions, release manifests and review history. | Record measured recovery and integrity results; do not promise RPO/RTO without agreed objectives and a successful drill.
Production gate | Day 28 is a go/no-go decision. Publishing requires passed tests/UAT, academic authorization, operational readiness and release-owner approval. | A failed gate leaves release blocked and triggers revised estimates; no automatic production go-live.
Traceability | Use BR-01?BR-36 and Developer Guide R3 requirements. Partial/deferred items remain visible in the backlog. | Add exact section/requirement mapping during Day 1; no claim of full BRD conformance for this MVP.
Review basis | BRD v3 and Developer Guide v3 dated 8 October 2026; both supplied Excel files; local LMS source inspected 15 October 2026. | Static review only: hosted state, cited completion evidence and full browser execution were not verified.

## Follow-up Backlog
ID | Follow-up scope / requirement | Dependency / exit evidence | Priority / timing
F01 | Isolated HTML single-file and ZIP package import with relative assets; supported provider embeds (BR-30/34). | Agree runtime origin, quarantine/inspection, traversal and archive limits, no host credentials, compatible sandbox, exact return state and reviewed fallback. | Next stage after secure MVP; estimate separately.
F02 | SCORM 1.2 single-SCO durable attempts; separate preview, Teacher demonstration and learner tracking. | Isolated runtime adapter, declared data model, acknowledged idempotent commits, resume and error/conformance fixtures. Review existing ScormPlayer/API wrapper before reuse. | After F01; estimate separately.
F03 | SCORM 2004 declared edition/profile and sequencing; multi-SCO if required. | Explicit agreed profile and independent conformance fixtures. SCORM 1.2 or simple HTML launch does not satisfy this. | Later stage; no compatibility claim before tests.
F04 | Collections, favorites and objective/misconception discovery filters (BR-31). | Membership-scoped favorites, non-copying references, paging, combined filter and leakage tests. | Next library increment.
F05 | Shared-resource dependency impact, explicit draft adoption and reauthorization (BR-33). | Visible-scope usage index; candidate?review?draft adoption?revalidate?authorize?new release; active runs unchanged. | Next governance increment; candidates never auto-replace.
F06 | Durable classroom evidence, reflections and Teacher feedback to Author work items (BR-36). | Pinned run/screen/binding context, observed/unobserved/incorrect distinction, consent/retention policy and role-safe records. | Next classroom increment.
F07 | Academic DOCX/PDF/Markdown/JSON imports and mapping review. | Source provenance/hash, missing/ambiguous field findings and explicit acceptance into drafts. No silent academic approval or content loss. | After draft contracts stabilize.
F08 | Full annotation/narration, richer branching, prerequisite graph and advanced object/layout support. | Reviewed object contracts, domain validation, accessibility, return-state tests and representative classroom QA. | Prioritize against BRD traceability gaps.
F09 | Upload quotas, resumable processing and operational scale/link-health automation (BR-35). | MVP already has basic limits/recovery; add representative-load, interrupted transfer, background job retry and health-monitor tests. | Before scaling beyond agreed pilot limits.
F10 | Advanced native simulations, 2D/3D activities, virtual labs, configured AI/provider search. | Scientific invariants/units, capability profiles, academic review, keyboard/static alternatives and configured provider/rights boundaries. | Explicit later acceptance gates.
F11 | Offline/export/import packages and broader rollout. | Exact manifest/asset pinning, private-content exclusion, withdrawal limitations, tested sync/recovery and target-device acceptance. | After online release/delivery is stable.
F12 | Full Rational Numbers migration (114 slides / 523 branches where actual source inventory confirms). | Access to reviewed source and rights; repeatable adapter; math/content/object/order/branch/role comparisons and academic approval. | After representative slice gate; estimate from inventory.

## Revision Notes
Area | Correction
Architecture | Removed pilot stack assumptions from the execution baseline; reuse existing LMS.
Scope | Explicit MVP boundary and separate follow-up backlog.
Status | Unverified completion claims no longer count toward verified progress.
SQL | Review/reuse existing Studio scripts and confirm actual migration state.
Security | Day 19 hardening supplements permissions required from the first implementation.
Release | Validation, exact academic approval, immutable manifests and pinned-run checks strengthened.
Migration | Representative source slice only; full 523-branch migration is separately gated.
Schedule | Provisional working-day sequence with capacity reforecast and same-day dependency rules.
Operations | Staging restore includes referenced assets; Day 28 is conditional go/no-go.
Inputs | Original workbooks retained unchanged; revised copy prepared on 15 October 2026.